## Project Overview
Project Details | Value
Project Name | ISO 27001 Risk Assessment & Compliance
Company Name | CloudFlow Technologies Pvt. Ltd.
Project Type | Practical Simulation
Framework | ISO/IEC 27001:2022
Objective | Identify risks and assess security controls
Tool Used | Microsoft Excel
Project Status | Completed

## Asset Inventory
Asset ID | Asset Name | Asset Type | Asset Owner | Confidentiality | Remarks
AST-001 | Customer Database | Database | IT Team | High | Contains customer information
AST-002 | Employee Accounts | User Accounts | HR Team | High | Contains employee information
AST-003 | Company Application | Application | IT Team | Medium | Used for business operations
AST-004 | Employee Laptops | Hardware | IT Team | Medium | Used by employees for work
AST-005 | Company Email | System | IT Team | High | Used for business communication

## Risk Register
Risk ID | Asset Name | Risk Description | Likelihood | Impact | Risk Score | Risk Level | Risk Treatment
RSK-001 | Customer Database | Unauthorized access to customer data | 4 | 5 | 20 | High | Mitigate
RSK-002 | Employee Accounts | Excessive user access permissions | 3 | 4 | 12 | Medium | Mitigate
RSK-003 | Company Application | Security vulnerability in application | 3 | 5 | 15 | High | Mitigate
RSK-004 | Employee Laptops | Loss of laptop containing company data | 2 | 4 | 8 | Medium | Mitigate
RSK-005 | Company Email | Phishing attack on employee email | 4 | 4 | 16 | High | Mitigate

## Risk Treatment
Risk ID | Risk Description | Risk Level | Treatment Strategy | Remediation Action | Responsible Team | Status
RSK-001 | Unauthorized access to customer data | High | Mitigate | Enable MFA for all customer database users | IT Security | In Progress
RSK-002 | Excessive user access permissions | Medium | Mitigate | Remove unnecessary access permissions | IT Team | Open
RSK-003 | Security vulnerability in application | High | Mitigate | Perform vulnerability assessment and fix identified issues | Application Team | Open
RSK-004 | Loss of laptop containing company data | Medium | Mitigate | Enable device encryption and remote lock | IT Team | Open
RSK-005 | Phishing attack on employee email | High | Mitigate | Conduct phishing awareness training and enable email protection | IT Security | Open

## Control Testing
Test ID | Asset Name | Security Control | Test Result | Evidence | Status
CTL-001 | Customer Database | Multi-Factor Authentication | Fail | MFA report shows 3 accounts without MFA | Open
CTL-002 | Employee Accounts | Access Review | Fail | Access review shows excessive user permissions | Open
CTL-003 | Company Application | Vulnerability Assessment | Pass | Vulnerability assessment report reviewed | Closed
CTL-004 | Employee Laptops | Device Encryption | Pass | Encryption status report reviewed | Closed
CTL-005 | Company Email | Security Awareness Training | Fail | Training report shows incomplete employee training | Open

## Evidence Tracker
Evidence ID | Related Control | Evidence Name | Requested From | Date Requested | Evidence Status | Review Result | Remarks
EV-001 | CTL-001 | MFA Status Report | IT Security | 2026-10-20 | Received | Fail | 3 accounts do not have MFA enabled
EV-002 | CTL-002 | User Access Review Report | IT Team | 2026-10-20 | Received | Fail | Excessive access identified
EV-003 | CTL-003 | Vulnerability Assessment Report | Application Team | 2026-10-21 | Received | Pass | Report reviewed
EV-004 | CTL-004 | Device Encryption Report | IT Team | 2026-10-21 | Received | Pass | Encryption verified
EV-005 | CTL-005 | Security Training Report | HR Team | 2026-10-22 | Received | Fail | Some employees have incomplete training

## Finding Tracker
Finding ID | Related Risk ID | Finding Description | Severity | Remediation Action | Responsible Team | Due Date | Status
FND-001 | RSK-001 | MFA is not enabled for 3 customer database accounts | High | Enable MFA for all customer database accounts | IT Security | 2026-10-31 | In Progress
FND-002 | RSK-002 | User has access beyond assigned job role | Medium | Remove unnecessary access permissions | IT Team | 2026-10-31 | Open
FND-005 | RSK-005 | Some employees have incomplete security awareness training | High | Complete training and retain completion evidence | HR Team | 2026-11-06 | Open

## Security Compliance Tracker
Control ID | Security Requirement | Evidence Reviewed | Result | Remarks
CMP-001 | Multi-Factor Authentication | MFA Status Report | Fail | 3 customer database accounts do not have MFA
CMP-002 | User Access Review | User Access Review Report | Fail | Excessive user permissions identified
CMP-003 | Vulnerability Assessment | Vulnerability Assessment Report | Pass | Assessment report reviewed
CMP-004 | Device Encryption | Device Encryption Report | Pass | Encryption status verified
CMP-005 | Security Awareness Training | Security Training Report | Fail | Some employees have incomplete training

## Dashboard
Metric | Count | Row Labels | Sum of Count
Total Risks | 5 | Controls Failed | 3
High Risks | 3 | Controls Passed | 2
Medium Risks | 2 | Total Risks | 5
Controls Tested | 5 | Grand Total | 10
Controls Passed | 2
Controls Failed | 3
Total Findings | 3